## Effort Estimation
Effort Size Mapping
[7 empty] | Size | PD | Notes
[7 empty] | XS | 1
[7 empty] | S | 2
[7 empty] | M | 4
[7 empty] | L | 7
[7 empty] | XL | 15
Scope |  |  | Content |  | Effort Estimation |  |  | PD |  | Sprint |  |  | Notes
Summary | Comparison with System Entry | Comparison Golden Standards | Task | SubTask | T-Shirt Size | SC | C | SC | C | Week1 | Week2 | Week3
AIDA IP AUTHENTICATOR
Discovery & Architecture |  |  | IP Inventory | Catalog & deployment patterns | S | x |  | 2 | 0
|  |  | Architecture Design | Tech stack & design decisions | S | x |  | 2 | 0
|  |  |  | Integration approach | XS | x |  | 1 | 0
SDK Development |  |  | Python SDK | Core library & decorator API | L |  | x | 0 | 7
|  |  |  | Token caching & renewal | M |  | x | 0 | 4
|  |  |  | Offline grace periods | S |  | x | 0 | 2
|  |  |  | Error handling | S |  | x | 0 | 2
|  |  | JavaScript SDK | Core library & API | L |  | x | 0 | 7
|  |  |  | Token management | M |  | x | 0 | 4
|  |  |  | Browser/Node support | M |  | x | 0 | 4
Validation Backend |  |  | Infrastructure | Serverless setup & DB schema | M |  | x | 0 | 4
|  |  | License API | Validation & JWT issuance | L |  | x | 0 | 7
|  |  | Telemetry | Usage pipeline & storage | M |  | x | 0 | 4
|  |  |  | Anomaly detection | S |  | x | 0 | 2
|  |  | Hardening | Rate limiting & security | M |  | x | 0 | 4
|  |  |  | Caching layer | M |  | x | 0 | 4
Admin Portal |  |  | Portal Setup | Framework & SSO integration | M |  | x | 0 | 4
|  |  | License Management | CRUD & revocation | L |  | x | 0 | 7
|  |  | Dashboards | Usage analytics & alerts | M |  | x | 0 | 4
|  |  | UI Polish | UX refinement | S |  | x | 0 | 2
|  |  |  | Export functionality | S |  | x | 0 | 3
Docs & Testing |  |  | Documentation | Integration guide & API docs | M | x |  | 4 | 0
|  |  | Testing | Unit & integration tests | M |  | x | 0 | 4
|  |  |  | Edge cases & E2E | M |  | x | 0 | 4
|  |  | Security | Security review | M | x |  | 4 | 0
|  |  |  | Pen testing coordination | M |  | x | 0 | 4 |  |  |  | External vendor
|  |  | TOTAL |  |  |  |  | 13 | 87 | 100 | PD
Business Case Summary
Total Investment | €50,000 |  | ~100 PD dev + €3k cloud + €2k security
Ongoing Costs | €300/month hosting |  | ~5 PD/quarter maintenance
Revenue Projections
6 months | €150,000 - €250,000 |  | Pilot licensing (2-3 AIDA solutions)
3 years (conservative) | €800,000 - €1,200,000 |  | Portfolio licensing + renewals + support
SaaS Monetization Potential |  |  | (Key growth lever)
Subscription model | €500-1,500/month/solution |  | Per-solution enterprise licensing
Usage-based tier | €0.01-0.05/API call |  | High-volume deployment pricing
Support contracts | €10,000-25,000/year |  | Premium SLA + priority support
3-year SaaS scenario | €1,500,000 - €2,500,000 |  | Full product conversion
ROI Indicators
Break-even | 4-6 months |  | First 2-3 client deployments
Engagement margin | 35-45% |  | Post investment recovery
Multiplication | All AIDA solutions |  | Build once, deploy everywhere
Strategic Value
IP Protection | High |  | Deterrence + detection + evidence
Client Control | Remote revocation |  | Contract enforcement capability
Upsell Path | Support → SaaS → Premium |  | Natural monetization ladder